## Sheet1
Status | Date Completed | Task ID | Description | Type | Priority | For Phase | Path | Commit Message | Has FE Changes | Has BE Changes | Remarks
Tour0028
|  | Tour0027 | As a tour creator, I should be able to Add/Remove tour photos after creation | Feat | High | 1
|  | Tour0026 | Require at least one photo when adding a new tour | Feat | Medium | 1
|  | Tour0025 | Implement logging functionality | Feat | High | 1
|  | Tour0024 | As a tour creator, I should be able to add schedules to my tour | Feat | High | 1
|  | Tour0023 | Remove 'See Photos' button link from tour list item beside View Details | Feat | Medium | 1
Completed |  | Tour0022 | As a user I should be able to see a tour's complete details with photos | Feat | High | 1
|  | Tour0021 | As a user, I should be able to request to join a tour | Feat | High | 1
|  | Tour0020 | As a tour creator, I should be able to add contact details to my tour (e.g. phone #, FB/Messenger, E-Mail, Viber) | Feat | High | 1
|  | Tour0019 | As a tour creator, I should be able to select a destination city/province | Feat | Medium
|  | Tour0018 | As a tour creator, I should be able to add title and description to photos when adding tour photos | Feat | Medium | 1
|  | Tour0017 | Add character counter to input fields with max length | Feat | Medium | 1
Completed |  | Tour0016 | Add client-side global error handler | Feat | High | 1
|  | Tour0015 | After submitting new Tour details, prevent "Are you sure you want to leave?" pop-up from showing when navigating to another page | Bug | Medium | 1
|  | Tour0014 | As a user, I should be able to set a profile picture which will be displayed beside my name in the header | Feat | High | 1
Completed |  | Tour0013 | As a user, I should be able to log in using my Facebook account | Feat | High | 1
|  | Tour0012 | As a user, I should see my name instead of my email address in the header | Feat | Low | 1
|  | Tour0011 | As a user, I should be able to delete tour details | Feat | High
In Progress |  | Tour0010 | As a tour creator, I should be able to edit my tour's details | Feat | High | 1
Completed |  | Tour0009 | As a user, I should be able to add tours and upload photos to the tour | Feat | High | 1
|  | Tour0008 | As a user, I should be able to see in the tour list item who added the tour | Feat | Medium | 1
|  | Tour0007 | As a tour creator, I should be able to add tags to indicate what activities are included in my tour (e.g. hiking, swimming, climbing, etc.) | Feat | Medium | 1
|  | Tour0006 | Fix scroll design | Design | Low | 1
|  | Tour0005 | Remove screen width indicator beside Website title | Refactor | Low | 1
|  | Tour0004 | Add account management pages | Feat | Low | 1
|  | Tour0003 | Implement email confirmation | Feat | Low | 1
|  | Tour0002 | TourListItem: use tile gallery to display tour photos | Feat | Medium | 1
Won't Fix |  | Tour0001 | Identity pages wouldn't load | Bug | Critical | 1
Note on F1: Critical - show stopper / causes further issues if not fixed immediately High - must be completed before deployment Medium - causes a bit of inconveniece/nice to have before deployment Low - not causing inconvenience / improvement / for phase 2

## Screens
Module
Tour
Edit Details
Add Details
List
Photos

## Values
Task Status
To Do
In Progress
Completed